BvLogic

CHECKLIST

BRD Review Checklist

| Document ID | BVL-0CADB5 |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 12 September 2026 |
| Next review | 12 September 2027 |
| Document type | Checklist |

Contents

Use this on a draft before circulating it. Pair with the

BRD template (bvlogic.com/templates/brd/) for the structure and the

BRD guide (bvlogic.com/pmo/brd/) for the reasoning.

Document: _______________  Version: ____ Reviewer: _______________  Date: _______

# 1. Purpose and framing

[ ] The business need is stated, not a solution

[ ] It is clear why now. What changed

[ ] The cost of doing nothing is stated

[ ] Someone reading it cold would understand what problem is being solved

# 2. Solutioning: the most common defect

[ ] No screens, fields, layouts or technology specified

[ ] No supplier or product named as a requirement

[ ] Where a solution IS mandated, it is recorded as a constraint, with who mandated it

A BRD that specifies the interface removes the design space before anyone has explored it, and

locks in the analyst's first guess. If a requirement describes a screen, ask what decision the

user is trying to make.

# 3. Requirements

[ ] Each has a unique identifier that will never be reused

[ ] Each is testable. You can say in one sentence how it would be proven

[ ] One requirement per statement, anything with "and" or "or" is split

[ ] No user-friendly, robust, scalable, intuitive, appropriate

[ ] Priority assigned, and not everything is "must"

[ ] Each traces to a business objective

Count the untestable ones: ____ of ____. Anything above zero is worth a conversation; a third of the document teaches everyone that requirements are decorative.

# 4. Scope

[ ] In-scope list present

[ ] Out-of-scope list present, and contains things people actually expect

[ ] Interfaces to other systems identified

[ ] Affected teams and processes named

The out-of-scope section is the cheapest dispute prevention available. "It will not cure cancer" is not the list; "it will not replace the existing approval workflow" is.

# 5. Non-functional requirements

[ ] Performance, with a number and a load condition

[ ] Volume and expected growth

[ ] Availability, and what it excludes

[ ] Retention and audit requirements

[ ] Accessibility standard named

[ ] Security and permissions model outlined

[ ] Personal data identified, with lawful basis

These surface late and are expensive to retrofit. Silence on them is a decision to discover them in production.

# 6. Assumptions, dependencies and risks

[ ] Assumptions listed, each with who confirms it

[ ] Dependencies on other teams or suppliers named, with owners

[ ] Top risks recorded and linked to the risk register (bvlogic.com/pmo/risk-register/)

[ ] Open questions listed with owners and dates

# 7. Usability of the document

[ ] Short enough to be read properly by the people approving it

[ ] Sections can be reviewed independently by the people who care about each

[ ] Terms used consistently, a glossary exists if the domain has jargon

[ ] Version, date and status on the front

Length is not a quality signal. A tight document gets read and its contradictions get found; a

long one gets approved and hides them.

# 8. Sign-off

[ ] Named approvers, not roles

[ ] No sign-off by silence. "no response by Friday means approved" produces approvals that

evaporate the moment something goes wrong

[ ] Baseline point agreed, after which changes go through

change management (bvlogic.com/pmo/change-management/)

[ ] Delivery and test have both read it before it is baselined

Involving test before baseline is the cheapest quality step available, they ask "how would I prove that?" about statements everyone else read straight past.

# Reviewer verdict

| Untestable requirements found |  |
| --- | --- |
| Solutioning found |  |
| Missing non-functional areas |  |
| Ready to circulate | yes / no |
| Blocking issues |  |

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.