BvLogic

CHECKLIST

Project Health Check

| Document ID | BVL-1D0E39 |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 12 September 2026 |
| Next review | 12 September 2027 |
| Document type | Checklist |

Contents

Run this monthly, or whenever something feels wrong and nobody can say what. It is written to

surface the things a status report smooths over.

Project: _______________  Assessed by: _______________  Date: _______

# 1. The direct questions

[ ] Is the current end date one you would personally bet on? yes / no

[ ] If no, has anyone been told? yes / no, when: _______

[ ] Does the plan reflect what is actually happening, or what was agreed months ago?

[ ] Would the team give the same answers as the project manager?

[ ] Has any deadline moved in the last quarter, and was that visible?

The most common failure in project reporting is not lying. It is a series of individually reasonable "we will catch up next sprint" judgements, none of which is ever escalated, until the gap is too large to absorb.

# 2. Scope

[ ] Baseline scope is written down and findable

[ ] Changes since baseline are recorded with their cumulative impact

[ ] Cumulative schedule impact of approved changes: ____

[ ] Out-of-scope list exists and has been used to decline something

[ ] Nobody is adding work informally to individual team members

# 3. Progress

[ ] Progress measured by completed, accepted work. Not by effort spent

[ ] "90% done" claims older than two weeks investigated

[ ] Testing is progressing alongside build, not queued at the end

[ ] Integration has been attempted, not deferred

[ ] The riskiest work was done early, not left until last

The oldest item still "in progress": ____ days

Deferred integration and deferred testing are the two most reliable predictors of a late project, because both hide accumulated problems until the point where there is no time to absorb them.

# 4. The queues

[ ] Average time to get a decision: ____

[ ] Average wait on an external dependency: ____

[ ] Items currently blocked: ____, oldest blocked for ____ days

[ ] Environments available when needed

[ ] Anyone waiting on a single named person for more than one thing

Delay usually lives in queues rather than in the work. If the team is waiting a week for decisions, no amount of delivery improvement changes the outcome.

# 5. People

[ ] Team members are on this project the share of time that was planned

[ ] Key-person dependency identified: _______________

[ ] Someone else could continue if that person left tomorrow

[ ] Overtime is not being used routinely to hold the date

[ ] Turnover since start: ____

Sustained overtime is a schedule problem being paid for with quality, and it shows up two months later as defects.

# 6. Quality signals

[ ] Defect count trending down, not up, as the end approaches

[ ] No large untested area

[ ] Non-functional requirements have been tested, not just functional ones

[ ] Known defects list exists, with severity agreed

[ ] Technical debt taken deliberately, and recorded

# 7. Governance

[ ] Sponsor is engaged, attended the last two reviews

[ ] Risks reviewed in the last fortnight, with overdue mitigations chased

[ ] Decisions are being recorded

[ ] Status reporting matches what the team would say

[ ] Bad news reaches the sponsor without being softened at each level

When did we last tell the sponsor something they did not want to hear? _______

If the answer is "never", the reporting chain is filtering, and the sponsor is making decisions on a version of reality that has been improved on the way up.

# Verdict

| Confidence in the end date | high / medium / low |
| --- | --- |
| The one thing most likely to derail this |  |
| What I would escalate today |  |
| Action, owner, date |  |

A health check that produces no action is a status meeting. Leave with one thing that changes.

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.