BvLogic

REPORT

Project Status Report: Sample

| Document ID | BVL-54D386 |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 12 September 2026 |
| Next review | 12 September 2027 |
| Document type | Report |

Contents

This is an illustrative example. The project and figures are composed to show what honest

reporting looks like when the news is bad, not drawn from a named engagement.

Project: Customer portal replacement Period: Month 8 of 12  Prepared by: Delivery manager  For: Sponsor

# 1. The headline

Would I personally bet on the current end date? No.

By how much: 6 to 9 weeks, on current scope.

Since when did I know: the trend has been visible for around six weeks. I am reporting it now having confirmed it against the numbers below rather than raising it as a feeling.

# 2. Progress

| Timeline elapsed | 70% |
| --- | --- |
| Budget consumed | 68% |
| Scope completed and accepted | 41% |

The first two numbers have been reported for eight months and are reassuring. The third has not been tracked until this period, and it is the one that predicts the end date.

Claimed "90% done" for more than two weeks: 3 items (payments integration, notification service, admin permissions).

# 3. What changed

| Period | Changes approved | Schedule impact |
| --- | --- | --- |
| Months 1 to 3 | 4 | +2 weeks |
| Months 4 to 6 | 7 | +5 weeks |
| Months 7 to 8 | 3 | +2 weeks |
| Cumulative | 14 | +9 weeks |

Cost impact cumulative: +£142,000. Scope removed to absorb any of it: none.

Each change was assessed and approved individually and each was reasonable. This is the first time they have been added up.

# 4. Blocked

| What | Blocked since | Waiting on | Escalate? |
| --- | --- | --- | --- |
| Payments integration | 61 days | Third-party API contract | yes, needs you |
| SSO configuration | 22 days | Internal security review | yes |
| Address lookup licence | 17 days | Procurement | yes |
| 3 further items | 14 to 19 days | Various | monitoring |

Average time to obtain a decision this period: 9 days.

The team works in two-week iterations. A nine-day decision means most iterations contain a stall, and the team has adapted by working around blockers rather than escalating them, which is why this has not surfaced in previous reports.

# 5. Quality

| Open defects | 34 (4 high, 18 medium, 12 low) |
| --- | --- |
| Trend | rising |
| Untested areas | payments, notifications, reporting |
| Integration attempted | no |
| Non-functional testing | not started |

Integration with the two upstream systems has not been attempted. Testing is scheduled to begin in month 10. Both are deferred risk rather than absent risk.

# 6. Decision needed this week

| # | Decision | Who | By | Cost of not deciding |
| --- | --- | --- | --- | --- |
| 1 | Reduce scope, or move the date | Sponsor | 15th | Both happen anyway, later and without a choice |
| 2 | Escalate the payments API contract | Sponsor | 12th | Adds ~1 week per week of delay |
| 3 | Delegate approvals below £10k | Sponsor | 15th | 9-day decision latency continues |

Options for decision 1, with what each costs:

Hold the date, reduce scope. Defer reporting module and 4 of the 14 approved changes.

Recovers ~5 weeks. Recommended.

Hold scope, move the date. New date: mid-March. No further cost beyond the extension.

Hold both. Requires 3 additional engineers by the 20th; onboarding cost means the net

recovery is roughly 2 weeks, not 6.

# 7. Next period

| Commitment | Confidence |
| --- | --- |
| Payments integration complete (if contract lands by 12th) | low |
| Notification service accepted | medium |
| Begin integration testing | high |

---

Why this report reads the way it does. The project has been green for four months on effort metrics while accepted scope fell behind. Nothing was concealed; the numbers that would have shown it were not being reported.

Three figures carry the whole report: 41% against 70%, +9 weeks of un-totalled change, and 9-day decision latency. Each was available months ago. The report now includes them by default so this cannot recur quietly.

See project management (bvlogic.com/knowledge/project-management/), the health check (bvlogic.com/knowledge/project-management/checklist/), the status report template (bvlogic.com/knowledge/project-management/template/), and the worked example (bvlogic.com/knowledge/project-management/example/) of the review that produced these numbers.

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.